## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
DEP2 - ESG scores
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-11-12 |  |  |  |  | november | [20 empty] | december
Scrolling Increment: | 0 | time axis 2022-11-12 to 2023-01-06
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-11-12 to 2023-01-06
Week 1
Opmaken plan van aanpak | Goal | Benjamin | 100% | 2022-10-24 | 4
Requirements bepalen | Goal | Liselot | 100% | 2022-10-24 | 4
Domeinmodel opmaken | Goal | Brent | 100% | 2022-10-24 | 4
Vragen klant opstellen | Goal | Ayoub | 100% | 2022-10-24 | 4
Postgres db opzetten | Goal | Benjamin | 100% | 2022-10-24 | 4
Data mariadb overzetten naar Postgres db | Goal | Benjamin | 100% | 2022-10-25 | 5
Week 2
Aanpassen requirements | Goal | Liselotte | 0% | 2022-10-31 | 2
Aanpassen domeinmodel | Goal | Brent | 0% | 2022-10-31 | 2
ERD aanpassen | Goal | Benjamin | 0% | 2022-10-31 | 2
Scraping code aanpassen | Goal | Ayoub Brent | 0% | 2022-10-31 | 3
Websites scrapen | Milestone | Liselot |  | 2022-11-03 | 14 | bar: 2022-11-12 to 2022-11-16
Week 3
Implementeren scores | Goal | Brent |  | 2022-11-07 | 3
TBD
Week4
TBD
To add more data, Insert new rows ABOVE this one